## Yes
LSAR Date | eReview (Yes / No / NA) | Agency | Division | Project | On-Prem or Off-Prem | Last Update | Updated By | Latest Status Summary
2020-05-14 | No | BPU | .eCharge | Point-of-sale rebates for EV buyers |  | 2021-09-20 | BXA | Asked myNJ team if they had been contacted by BPU since 8/16
|  | MVC |  | Secure Uploads |  | 2021-10-20 | BXA | Ted says project is reviving
|  | OAL |  | CMS Upgrade for OAL |  | 2022-06-21 | SS | No response from them, but they appear to be prepping for LSAR (email exchange with SARMeeting)
2022-02-10 | No | DOT |  | Outdoor Advertizing ePermits eCheck |  | 2023-06-12 | RL | Meeting scheduled for 6/13
2022-05-26 | No | TRE | Pensions | Statistical Analysis software - IBM SPSS |  | 2023-06-20 | SS | 6/20/2023 - Emailed the project team, cc Kevin asking for implementation details - Debra responded, will work with SMEs and provide details to us.
2022-06-02 | No | TRE | DORES | TRE DORES Charon Vax for OMB IPB Project |  | 2023-06-19 | SS | awaiting the OIT approvals before it goes to a PO and is sent to the T3121 contract reseller.
2022-07-28 | No | DOT |  | Advanced Traffic Mgmt System - iNET |  | 2023-05-31 | SS | 5/31/2023 - Checked in again
|  | MVC |  | MCS Server & Software Upgrade Project |  | 2023-08-07 | BXA | Asked Na for most recent diagram
|  | OIT |  | Clear Skye IGA Proof of Concept |  | 2023-07-24 | BXA | kickoff meeting on Aug 3rd, there were 2 issues needed to be handled by OIT, one is done; other one is in the works
2022-11-10 | Yes | DEP |  | Motorola Body Worn Cameras Project |  | 2023-08-07 | JC | Created a new diagram and submitted to Jim M at DEP for approval / changes to be made.
2023-04-12 | Yes | AGR |  | SADC eFarms |  | 2023-08-07 | SS | Mark replied, we asked some follow-up questions
2023-04-28 | Yes | DCA |  | Resource Management Tool - Codes by Fire File |  | 2023-07-25 | SS | 7/24/2023 - Rashid said PO sent, asked him to clarify.
|  | TRE | Pensions | Innowake POC (Deloitte Vendor) |  | 2023-07-24 | BXA | Set-up still ongoing - Azure DevOps placement being discussed
2023-05-12 | Yes | OAL |  | Client Management System |  | 2023-06-21 | SS | 6/21/2023 - Checked in
2023-05-11 | Yes | OPD |  | Discovery Evidence |  | 2023-07-11 | SS | 6/30/2023 - Last communicated to Aparna to let us know when procurement is completed
2023-05-25 | No | DOS |  | Cannabis Training Academy |  | 2023-07-20 | SS | 7/20/2023 - Asked Krishna if he got responses from vendor to Allison’s questions.
|  | DOH |  | UVIS updated C-LSAR form & Visio system diagram |  | 2023-07-24 | RL | Next check in with David F to be done 3/31
2023-05-01 | Yes | DOC |  | Remote Digital Signs - AppSpace |  | 2023-07-26 | RL | Vendor is NOT on contract, Last report update dated as: 7/17/2023
2022-05-26 | No | Lottery |  | Certified Mail Software Project |  | 2023-07-26 | RL | Asked Shaiesta if she saw Rick P's question on compensating controls that other Quad customers use?
2023-06-05 | Yes | DOT |  | Primavera P6 Upgrade |  | 2023-07-18 | RL | POKE email sent out.
2023-07-13 | No | DOH |  | Learning Management System (LMS) – SABA |  | 2023-08-14 | RL | Don Eckel sent - Going Live - 8/16
2023-07-19 | Yes | LWD |  | IMPLAN Economic Impact Software
2023-08-09 | No | OSHE |  | Sage Grant Management System |  | 2023-08-14 | SS | LSAR follow-up sent
2023-07-27 | No | DOC |  | Video Teleconferencing (VTC) Updates |  | 2023-07-31 | RL | Going to present project next A&S meeting 8/15/23

## No
LSAR Date | Department | Project | Design Needed? | Notes
2017-05-11 | DHS | NeoPost Doc. Insertion | N
2017-05-25 | DOT | Litigation Hold | N
2017-06-08 | MVC | O365 | N
2017-06-08 | DORES | RIMS (Record Info Mgmt. Sys) | N
2017-06-22 | DOT | Adaptive Projects | N
2017-07-13 | DHS | NJ-IRMS | N
2017-07-27 | DOT | Think Smart Workflows | N
2017-08-24 | DORES | Public Record Amendments | N
2017-09-14 | OIT | DocuSign | N
2017-09-28 | DOT | NexusWorks | N |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\DOT\NexusWorx.docx
2017-10-26 | DOH | Early Intervention Management System | N | Hosted by PCG
2017-10-23 | DCF | Scholarship Fund Donations
2017-12-14 | OIT | EO 225 - APEX Asset & Staff Tracking | N
2017-12-14 | DOC | Drones | N
NA* | DHS | SNAPtrac/NJHelps/iTAMS |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\DHS\oneapp-snaptrac-fw-rule.docx
2018-04-12 | DOH | Illumina Next-Gen Sequencing | N
2018-07-26 | DOH | Snap-Ed | N
2018-12-13 | OHSP | Crowdstrike | N
2019-05-30 | OHSP | NJCCIC Member Portal | Y | N | N | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OHSP.NJCCICMemberPortal\NJCCICMemberPortalSTATUS.docx
** | OIT | ADF Print server replacements | 2019-11-08 | BA | Splunk will ingest logs and develop report of inbound users
**** 9/21/2021 | DOT | NexxusWorx | 2021-09-27 | JC | No need for a design or Cloud IR, new licenses were purchased - no architectural c hanges.
2023-06-27 | BPU | Charger Data Aggregation Project | No | BXA

## Done
LSAR Date | eReview (Yes or No) | Agency | Division | Project | on-prem or off-prem | Last Update | Updated By | Latest Status Summary
2016-02-25 |  | LWD |  | eLITS
2016-12-08 |  | DCF |  | Child Care Quality - eXpedite |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\DHS.ChildCareQuality\eXpedite.docx
2016-12-22 |  | AG |  | SNEARS2.0 |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\Ag\SNEARS2.0.docx
2017-05-11 |  | OIT |  | Apex
2017-05-11 |  | DEP |  | Campground reservations
2017-06-08 |  | OIT |  | Biz Objects 4 migration
2017-06-22 |  | OIT |  | Datastage
2017-07-13 |  | Ag |  | VADDS-LIMS |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\Ag\TheStoryOfVADDS.docx
2017-07-27 |  | DRBC |  | Forklift to HUB project |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\DRBC\P2V_Forklift2HUB.docx
2017-08-10 |  | DHS |  | ePay for Licensing |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\DHS\ePayLicensing.docx
2017-08-10 |  | OMB |  | eIWO |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.OMB-eIWO\eIWO_IncomeWitholding-STATUS.docx
2017-08-24 |  | DHS |  | Document Imaging Management Sys (DIMS)
2017-08-24 |  | DOH |  | Element LIMS
2017-08-24 |  | DOT |  | AASHTONWARE (formerly PONTIS) |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOT.PONTIS\AASHTONWARE_formerly_Pontis-STATUS.docx
2017-09-14 |  | DOBI |  | Win Magic |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\DOBI\DOBI-WinMagic.docx
2017-09-14 |  | DOT |  | DOT Traffic Ops |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOT.TrafficOps\TrafficOps_VXRail-STATUS.docx
2017-09-21 |  | DOH |  | PerkinElmer Specimen Gate |  |  |  | Info received from Darrell Booker; sent email to PMO (Rob C) and Darrell confirming validation on 9-26-17
2017-09-28 |  | LWD |  | BARTS 2017 - IRME |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LWD.BARTS-IRME\BARTS-IRME-STATUS.docx
2017-09-28 |  | Pensions |  | Oracle Siebel CRM |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.Pensions-OracleChat_SiebelCRM\OracleChat_SiebelCRM-STATUS.docx
2017-10-12 |  | LWD |  | Loops Data Cleansing |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\LWD\LOOPS-DataCleanse.docx
2017-10-12 |  | OMB |  | Recon Art Replacement |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OHSP\ReconArt.docx
2017-10-12 |  | LWD |  | Labor Rational Asset Analyzer |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\LWD\RationalAssetAnalyzer.docx
2017-10-23 |  | OHSP |  | Imperva Incapsula |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OHSP\ImpervaIncapsula.docx
2017-11-20 |  | OIT |  | RV300ComputerRoomMigration |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OIT\Migration2HUB.docx
2017-11-30 |  | OAL |  | CMS - MS Dynamics 365 |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OAL\CMS-MSDynamics365.docx
2017-12-07 |  | DORES |  | Corporate Business Tax Application |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\Treasury\DORES\CBTApp\CBT-NICApp.docx
2018-01-11 |  | OIT |  | eCats mobile |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OIT\eCatsMobile.docx
2018-01-11 |  | L&PS |  | eGrants |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LPS.eGrants\eGrants-STATUS.docx
2018-02-08 |  | NJSP |  | NJSP Firearms application online
2018-02-22 |  | CBVI |  | Aware CMS Implementation |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\CBVI.OhNoIts-AWARE_CMS\CBVI-AWARECMS-STATUS.docx
2018-03-08 |  | DEP |  | Emergency Contact Update System |  |  |  | Closed
2018-03-22 |  | DOT |  | WinkForge Camera Infrastructure expansion |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOT.WinkForge-Camera-Expansion\WinkForge-Expansion-STATUS.docx
2018-03-22 |  | LWD |  | Wage and Hour Ag Mobile Inspection App |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\LWD.WageHourAgMobileInspectionApp\LWD-AgInspectionApp.docx
2018-05-10 |  | DORES |  | Gov2Go |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.DORES-Gov2Go\Gov2Go.docx
2018-05-24 |  | DHS |  | Universal App Processing |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\DHS.UniversalAppProcessing\DHS-UniversalAppProcessing.docx
2018-06-14 |  | Pensions |  | Board Election Project |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.Pensions-BoardElectionProject\TRE.Pensions-BoardElectionProject.docx
2018-06-28 |  | LWD |  | Trade Act |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LWD.Trade Act\LWD-TradeAct.docx
2018-07-12 |  | MVC |  | EDDL Database Encryption at Rest (Ideamia) |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\MVC.Pframe-migration-Idemia\MVC-EDDL-DIR-FRS-dbEncryption.docx
2018-08-23 |  | DCF |  | CARI Checks |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DCF.CARIChecks\DCF.CARIChecks.docx
* |  | OHSP |  | Vulnerability Management Zone
* |  | OIT |  | Citrix XenDesktop |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\OIT.CitirixXenDesktop\CitrixXenDesktop.docx
** |  | Pensions |  | SoNJ/Horizon migration from SNA to TCP/IP |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.Pensions-HorizonSNAConnexMigration\MigratingSNA-to-TCPIP.docx
*** |  | LWD |  | TWES migration (Glassfish to JBOSS) |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LWD.TWESMigration\LWD-TweezerSTATUS.docx
**NA |  | ELEC |  | eFile365 |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\ELEC.eFile365\eFile365-STATUS.docx
N/A |  | OIT - PMO |  | Service NOW! - Additional Mid Server VMs |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OIT.PMO-ServiceNOWMoreVMs\OIT.PMO-ServiceNOWMoreVMs.docx
N/A |  | DOT |  | Sharepoint OneDrive Migration Resting Point |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OIT.SharePointMigrationSpace\DOT-Sharepoint-Migration-Resting-Point-STATUS.docx
NA |  | OIT |  | McAfee EPO extension |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OIT\EPO_extension.docx
|  | OHSP |  | Proofpoint upgrade |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\ActiveProjects\AAA_Status\StatusLinkedNotes\OHSP\ProofpointMigration.docx
|  | DOE |  | NJ EASEL
|  | LWD |  | 55+ Salesforce |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\LWD.55Plus\LWD.55Plus.docx
2018-04-12 |  | DOT |  | Safety Voyager |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOT.Safety-Voyager\DOT.SafetyVeeger-STATUS.docx
2018-12-13 |  | DORES |  | NJ-1040 Online Filing |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.DORES-NJ1040-Online-Tax-Filing\TRE.DORES-NJ1040-Online-Tax-Filing.docx
2019-01-24 |  | TRE.DPB |  | Pensions TYP_ePay |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\TRE.DPB-Pensions-TYP-ePay\DBP-TYP-ePay-Status.docx
2019-01-10 |  | DOBI |  | Real Estate License Combine |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitectureActive Projects\DOBI.RealEstateLicenseCombine\DOBI-RealEstateLicenseSTATUS.docx
N/A |  | DOT |  | Estip (TELUS) |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOT.TELUS\DOT.TELUS-STATUS.docx
N/A |  | OIT |  | Citrix VDI POC |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OIT.Citrix-VDI\OIT-VDI-STATUS.docx
2019-01-24 |  | TRE.TAX |  | Taxation Business Tax Credits Application |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\TRE.TAX.BusTaxCreditsApp\TRE.TAX.BusTaxCreditsApp.docx
2018-10-29 |  | OHSP |  | MoveIT File Transfer (Datamotion replacement) |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OHSP.MoveIT\OHSP.MoveITStatus.docx
2019-02-04 |  | OIT |  | Qualtrax migration from Ag to HUB
2018-01-25 |  | L&PS |  | Evidential Breath Testing System |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LPS.EvidentialBreathTesting\EvidentialBreathTestingSystem-STATUS.docx
** |  | OIT |  | Solarwinds - Zenoss replacement |  |  |  | Closed Projects\OIT.Solarwinds-Zenoss Replacement\SolarwindsSTATUS.docx
2018-09-13 |  | LWD |  | WHATS field module |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\LWD-WHATS-FieldInvestigationModule\WHATS-FieldModule.docx
2019-04-11 |  | MVC |  | Point of Sale replacement D365/triPOS/NICUSA
2017-10-26 |  | DOH |  | VERIS NJ |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DOH.VERIS_NJ\VERIS_VeryNJ-STATUS.docx
2017-11-09 |  | OIT |  | State Wide Active Directory Consolidation |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\OIT.AD-Consolidation\Statewide-AD-Consolidation-STATUS.docx
2019-04-25 |  | OIT |  | NJGIN 3
2018-11-15 |  | LWD |  | Self-Service Replacement- Job Zone |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\LWD.JobZone-OSOS\JobZoneStatus.docx
2019-04-11 |  | Treasury |  | DSTREAM Application Upgrade / Migration to Exadata |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\TRE.DSTREAM\DSTREAM-ProjectStatus.docx
2019-05-23 |  | DCF |  | Alert Media / Safe Signal Worker Safety |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DCF.AlertMedia\AlertMediaSTATUS.docx
2019-06-27 |  | DEP |  | ARinspection |  |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DEP.ARinspection\ARinspection-Status.docx
|  | TRE/DORES |  | Affirmative Action Application Database Migration to Exadata |  |  |  | Active Projects\TRE.DORES-Affirm_Action_DB_Exadata\Affirmative Action Application Database Migration to Exadata.docx
|  | DOL/LWD |  | Data Gateway for Power BI |  |  |  | 9/5 – Project was presented at Validated Design meeting
2019-06-13 |  | DOH |  | REDCap |  |  |  | 9/5 – Presented at Validated Design meeting
2019-05-30 |  | DOH |  | UVIS Migration from OAG to OIT HW at Hub |  | 2019-07-18 | JC | UVIS STATUS
|  | DOE |  | Generate - automates / simplifies reporting |  | 2019-09-13 | JC | 9/13/2019 Sent a follow up to Leo for information confirmation; also followed up on original email
2019-01-10 |  | DOH |  | EOHAP FoxPro Conversion |  |  |  | EOHAP-STATUS
2019-06-27 |  | TRE.ODI |  | Supplier Diversity Tracking & Dashboard (B2Gnow) |  | 2019-10-16 | BA | Hester might want some follow-up, but design is done
2019-09-12 |  | OIT |  | ArcGIS Monitor Implementation |  | 2019-09-16 | JC | LSAR held on 9/12. GIS group to re-send LSAR diagram in Visio format
2019-05-09 |  | DCF |  | FCP/DOW Information and Reporting System |  | 2019-09-30 | BA | 9/30/2019 - myNJ team and vendor are working to configure SAML
2019-05-09 |  | LPS/OAG |  | Bias Reporting |  | 2019-11-08 | JC | Design is validated; asked Rich Chelenza to confirm TCP port of Dynamics Odata connector (REST web service for Infoshare to pull data) - UPDATE - It WILL use port 443.
|  | DCF |  | Modular NEICE CMS |  | 2019-11-13 | RL | Tue 11/12/2019 11:33 AM – emailed Chris: contact info for Capacity Planning (zones/VMs)
2019-08-20 |  | DOT |  | Motorola - Emergency Oprs center |  | 2019-11-22 | JC | Barry Approved the design on 11/20/2019.
*** |  | DHS |  | Salesforce - Conduent Extranet via the GSN |  | 2019-11-25 | SS | (BA - Can be moved to Done) November 2019 – Through working with Herminio Navarro (Bebet) on a DHS/DOBI project, we learned that DHS bought Conduent new F5s!
2019-11-14 |  | AGR |  | Summer Food Service Program |  | 2019-12-06 | SS | 12/5/2019 – Validated design held, general agreement, sent next steps to Mark
2019-07-25 |  | DOT |  | ATSPM (Automated Traffic Signal Performance Measurement System |  | 2019-12-16 | JC | Will present at the 12/19 validated design mtg - get Sai and / or Sulabh to designate zone names
2019-09-12 |  | TRE/DPP/DSS |  | ERP - Warehouse Management System |  | 2019-12-16 | JC | Conference call held on 12/13; will show to Steve 12/17 and present on 12/19
|  | DOC |  | Body Camera project |  | 2020-01-13 | JC | Asked SAR team if a PSAR is necessary
2019-10-10 |  | CSC |  | SABA New Learning Platform |  | 2020-02-07 | RL | completed validated design 2/6/2020
2019-12-17 |  | OIT |  | Dynatrace upgrade |  | 2020-02-07 | SS | 2/6/2020 – Validated design meeting held, capacity planning, network folks aware of planned build
2019-05-23 |  | TRE/UPA |  | Wagers to KAPS (SaaS) Migration |  | 2020-02-18 | RL | 2/12 - Final interface definition completed, diagram is all set for ISO review; 2/14 Kelmar working w/ PortalAdmin
*** |  | DOS/Elections |  | Voter Registration System/Voter portal |  | 2020-02-24 | SS | 2/21/2020 – Steve approved the design. Sent email connecting team to SAR and WebService teams for next step.
*** |  | OIT |  | Raiders of the CyberArk |  | 2020-01-10 | BA | January 7 - 9 – Team attended the CyberArk vendor training
2020-01-23 |  | DOS/MPTC |  | Production Services Directory Application |  | 2020-03-05 | SS | 3/3/2020 – Steve okayed.
2019-10-10 |  | LWD |  | SAGE IGX Upgrade (IGX = IntelliGrants, ver X) |  | 2020-03-02 | RL | Ann Lord concurred with our version of diagram. We are ready to validate with Steve!!!
2019-09-26 |  | DOC |  | Grants Management Software Platform System |  | 2020-03-10 | RL | Tuesday 3/10/2020 – Roger sent GrantVantage team message to proceed with the Hybrid C-IR form.
2020-01-09 |  | DHS |  | ImageTrust in Saleforce for Universal app |  | 2020-01-10 | BA | Diagram ready for review
2020-01-09 |  | DCA |  | Pluralsight training subscription |  | 2020-04-20 | BA | myNJ is being used
2020-05-14 |  | TRE/Pensions |  | Pension Employer Forms application |  | 2020-06-09 | SS | 6/2/2020 – BA got the ok from Steve for this, have let Bogdan know.
2020-04-09 |  | DOS/Elections |  | Voting Machine Tracking system |  | 2020-06-11 | SS | VMTS_STATUS
2019-03-14 |  | OHSP |  | Qradar SIEM Replacement - CHRONICLE |  | 2019-04-17 | BA | JC to clean this up, finalize notes
*** |  | AGR.CACFP |  | Mystery Firewall Rule |  | 2020-06-10 | BXA | One last check, then we remove the rule!
*** |  | OIT |  | IBM ILMT |  | 2020-05-22 | BXA | Lisa and team given test zone - INT-SVC-ILMT-TEST
2019-12-05 |  | LPS/OAG |  | BMS Secure Forms Portal |  | 2020-07-27 | SS | 06/17/2020 – C-IR went out. Emailed Hagen et al. - BA
*** |  | OIT.HATS |  | Host Access Transformation Service |  | 2020-06-22 | BXA | Project in PSAR, some complaint about diagram
|  | LWD |  | UI Call Center |  |  |  | Michelle says ACL policies complete; get diagram from Dan
2020-06-11 |  | DCF |  | NJSpirit - myNJ for External Partners |  | 2020-07-27 | SS | PSAR has been submitted
2019-11-20 |  | DOC |  | Collaboration - Inmate Video Teleconferencing |  | 2020-08-21 | SS | Aug 18, 2020 – Sent final note to Gary, Cap Planning, Sai, SAR advising of validated design.
*** |  | TRE.Admin |  | CPO Sorter |  | 2020-07-13 | BXA | Sent follow-up email
|  | OIT |  | MOVEit |  | 2020-08-14 | SS | 8/12/2020 - Sent diagram back to Dave with responses to his queries.
*** |  | DCF |  | Congregate Care COVID tracker |  | 2020-06-22 | BXA | Brian from GIS will update us once built
|  | LWD |  | WorkersComp App server migration |  | 2020-08-21 | SS | 8/19/2020 - Sent executive summary to Denise Reed.
2019-09-26 |  | DOC |  | Central Transport CAD (computer aided dispatch |  | 2020-09-22 | RL | Tue 9/15/2020 3:29 PM – emailed Gary: Validated Design completed so the next phase in SAR for the Central Transport CAD project is the PSAR
2020-02-27 |  | TRE/Pensions |  | Health Benefits Online/BusinesSolver |  | 2020-09-18 | SS | John okayed port with caveat. Bogdan said he will communicate with Network about port.
2020-08-13 |  | TRE/DORES |  | S Corp Election |  | 2020-09-16 | SS | 9/15/2020 - Security gave their blessing
?? |  | DEP |  | GIS Server upgrade |  | 2020-09-16 | SS | 9/11/2020 - VD meeting held per Maryann/Macready request; Denise/Kiczek ok!
e-Review closing date 9/15 |  | MVC |  | Multli-Scheduling Replacement |  | 2020-09-25 | RL | Mon 10/5/2020 10:55 AM – SARMeeting email E-Review started
?? |  | DEP |  | EmergencyContactMgmtSystem |  | 2020-09-23 | RL | 10/6/202 11:34 AM - Rob's email to DEP: "the recap will be going out later today."
?? |  | DOH |  | Web Proxy server upgrade - CDRSS,EDRS, Hippo |  | 2020-10-02 | RL | 9/25/2020 - Project now in Cap Planning, Roger sent out email / Sharon emailed Denise & John the diagrams
2020-09-24 |  | DOH |  | NJIIS Enhancements |  | 2020-10-02 | RL | Fri 9/25/2020 4:23 PM – Sharon emailed Denise & John the diagrams
None |  | OIT |  | Cisco Umbrella |  | 2020-09-28 | SS | 9/29/2020 - Received nice diagram, BA directed them to next step, IR
2020-09-10 |  | AGR |  | AG CARES 2.0 Project |  | 2020-09-25 | RL | 10/13 - meeting to review system diagram with Denise & John
2020-08-13 |  | LWD/DOL |  | eAdjudication (Salesforce- Employer) |  | 2020-09-18 | RL | 9/18/2020 8:38 AM: Reply from Jennifer Rose Quinn -> Thank you. We are clearing up some loose ends in the design and will complete this as soon as we have the design finalized.
|  | TRE/DPP |  | DocuSign - Urgent |  | 2020-08-25 | BXA | DORES and myNJ working to do SAML integration
2020-08-27 |  | DOE |  | Migrant Student Reporting - MIS2000 |  | 2021-01-21 | SS | Reminded Michael and Shashi about myNJ integration, to start conv. with Portal.
2019-03-14 |  | DOT |  | EDT Crash reports |  | 2020-10-15 | BXA | After email corre. with Chris Z., asked for design
|  | OIT |  | AWS Circuit |  | 2020-07-28 |  | received diagram from Andy Tram
** |  | DEP |  | NJEMS-LargeAttachments |  | 2020-10-26 | BXA | Russ sent a diagram. Will get it reviewed.
CapPlan |  | MVC |  | DARTSS |  | 2020-11-10 | SS | Nov 4, 2020 – Networking and Capacity Planning have received specs and working on it.
|  | LWD |  | EO-192 Violations application |  | 2020-11-09 | SS | BA helpd them get to Playbook stage
2020-10-07 |  | LPS |  | L&PS NJSP Qualtrax Compliance Software Project |  | 2020-12-03 | RL | 12/9 - email sent w/ C-IR form - Validated Design is complete - next steps
eReview 9/28 |  | DOC |  | DOC Edmentum |  | 2020-12-10 | RL | 12/10 – email sent w/ C-IR form - Validated Design is complete - next steps
CapPlan |  | DOT |  | InTune/BitLocker Encryption |  | 2020-11-10 | SS | BA had a talk with Steve P.
eReview 12/15 |  | OHSP/NJCCIC |  | NJCCIC Conference Platform (Zoomies) |  |  |  | STATUS DOC HERE
eReview 10/27/2020 |  | TRE |  | GCADA Online Grant System |  | 2021-01-05 | SS | 1/5/2021 – Presented to John K., OK. Sent out hand off email to team
2020-08-27 |  | DOT |  | Genetec Security Center C-LSAR |  | 2021-01-08 | SS | 1/7/2021 – Validated Design meeting, and handover to Cap Planning, networking.
eReview 1/6/21 |  | AG |  | Sire Stakes and Standardbred Dev Fund |  | 2021-01-15 | RL | On Schedule with Denise & John for Tues 1/12
2020-10-08 |  | TRE/DRM |  | Accident Reporting Portal |  | 2021-01-12 | SS | 1/12/2021 - Present to Security
eReview 12/23 |  | L&PS |  | Secure Remote Access (Zscaler) |  | 2021-01-15 | JC | 01/12/2021 - Asked Hagen to intervene
? |  | OIT |  | Carbon Black |  | 2021-02-22 | BXA
2021-02-11 |  | DOH |  | EBT for WIC |  | 2021-02-26 | JC | Design is validated.
2021-02-11 |  | NJSP |  | Personal Record Request |  | 2021-03-01 | SS | 2/17/2021 - Design validated, team informed.
eReview 12/16 |  | BPU |  | E-Dockets Phase II - Public Comments and Subscription |  | 2021-02-22 | BXA | Ready to show Denise and John
|  | LWD |  | Migrate JBOSS env |  |  |  | 2/18 - Zones defined
2021-02-23 |  | DOC |  | Axon Body Worn Cameras |  | 2021-03-01 | BXA | 3/3/2021 - Rediagramed their design, still waiting on some answers
|  | DOE |  | Student reporting - continue to f/w re. security exception |  |  |  | They are meeting with Portal 3/4/21, we are invited (done but still on radar)
2021-02-25 |  | DOC |  | CASAS |  | 2021-02-26 | RL | DOC responded to Roger's inquiry for a Visio plus questions.
N/A |  | TRE/DPMC |  | Tririga Upgrade Project |  | 2021-03-18 | JC | Validated at the 3/18/2021 Validated Design Meeting
*** |  | OIT |  | Oracle Cloud at Customer |  | 2021-01-19 | BXA | Scheduled migration form meeting, got answers from
2021-03-03 |  | MVC |  | Driver Video Conferencing Project |  | 2021-03-22 | BXA | Dominique sent over more info
2021-01-14 |  | DOT |  | Dameware Remote Access (was Bomgar/BeyondTrust) |  | 2021-04-12 | SS | 4/6/2021 - Design validated
2021-01-28 |  | LPS/NJSP |  | Expungement Database |  | 2021-04-09 | RL | Fri 4/9/2021 3:36 PM – Roger sent “Validated Design is complete” message to project team.
eReview 4/20/2021 |  | AGR |  | Core One TraceFirst Animal Disease Tracking Project |  | 2021-04-26 | RL | Design was validated on 4/29/2021
eReview 4/15/2021 |  | DHS |  | Secure Remote Access (Zscaler) Project |  | 2021-04-23 | JC | Zscaler-DHS-STATUS
eReview 3/31/21 |  | DCF |  | Connex Kinship Navigator Program (KNP) |  | 2021-04-27 | SS | 4/27/2021 - Created new Visio diagram, asked DCF to talk to Portal for myNJ
2021-02-25 |  | DHS/DMAHS |  | Member ODS |  | 2021-04-23 | JC | DHS-DMAHS-MemberODS_STATUS
2020-10-22 |  | LWD |  | Special Compensation Systems Redesign |  | 2021-05-21 | JC | Data In-Transit is encrypted along with the data at-rest.
2021-04-22 |  | DOH |  | Orchard Harvest - Copia Project |  | 2021-06-07 | RL | Mon 6/7/2021 9:15 AM - response from Heather Haywood <hhaywood@orchardsoft.com> regarding the question about the WAF
****No LSAR |  | LWD |  | Employee Relations Tracking system |  | 2021-05-25 | SS | Peter confirmed he is okay with subnet 10.6.241.x. Will send out handover, to move to next step.
2020-12-10 |  | LWD |  | NJ Career Network |  | 2021-01-25 | BXA | Spoke with Shravani and Chris C.
2021-05-27 |  | DOE |  | Electronic Automation and Signature Solution Mgmt (SimpliGov) |  | 2021-06-15 | JC | SIMPLIGOV STATUS
2021-04-08 |  | TRE.DPMC |  | HVAC Control Systems |  | 2021-06-14 | JC | Joe Oliver confirmed the acceptability of the proposed zone names - waiting on Dave Everett to approve design
2021-04-08 |  | DOT |  | Cisco Edge Intelligence |  | 2021-07-15 | SS | 7/15/2021 - Sent validation completed email to project team, sent FYI email to Mike R and Shaiesta.
2021-06-24 |  | DOH |  | Clinical Lab, Blood Bank, and Milk Bank Licensing |  | 2021-07-15 | SS | 7/14/2021 - Abhishek sent back really nicely compiled documents of revised diagrams and response.
... |  | DOH |  | JIRA/Trello plug-in for outlook |  | 2021-08-04 | BXA | JIRA_STATUS
2021-07-08 |  | DOT |  | Avigilon EntraPass |  | 2021-07-26 | BXA | Meeting scheduled for 7/29
2021-07-22 |  | LPS/DGE |  | L&PS Enterprise Law Management (ELM) |  | 2021-07-26 | JC | We will show this to Denise and John on 8/3. Every system component is internal to LPS.
eReview 4/1/21 |  | DOH |  | Health Screening Data Collection System (OxBow Med-IT® platform) Project. |  | 2021-07-30 | JC | OxBow_Status
2021-08-12 |  | MVC |  | BLS Request Digital Scanning and Retrieval (CGV notices) Project |  | 2021-08-13 | JC | We will show this to D and J on Tuesdee - SFTP connection to RR Donnelley is all that is needed
NA |  | MVC |  | AAMVA Migration |  | 2021-08-12 | JC | We will show this to D and J on Tuesdee - Hagen said to go ahead without the billing requirement
2021-04-22 |  | LWD |  | ID.me |  | 2021-08-23 | JC | Followed up with Kelly S. - already in prod but need diagram for our documentation
2020-12-03 |  | Pensions |  | Oracle Chat |  | 2021-08-23 | BXA | Demo scheduled for 08/24
2021-08-26 |  | CRC |  | Cannabis Licensing System Project |  | 2021-08-30 | JC | Design Validated - 08/31/2021
2021-07-22 |  | DCA |  | ARP Arrearage Utility Assistance project |  | 2021-08-30 | SS | 8/30/2021 - Discussed design internally, can show J & D tomorrow
2021-08-26 |  | OIT/OI |  | Business First Stop |  | 2021-09-07 | BXA | Gathering info on connexes and security requirements.
2021-09-09 |  | TRE/UPA |  | NICUSA eCheck payment portal |  | 2021-09-20 | SS | 9/14/2021 - Standard NICUSA ePay module. Show to D&J - they are fine
eReview 8/30/2021 |  | LWD |  | Appointment Self Scheduling System project |  | 2021-09-27 | SS | 9/21/2021 - Showed Denise and John, all good.
eReview 9/20/2021 |  | TRE/DPMC |  | Contract Classification Application system |  | 2021-09-20 | JC | Will show to Denise and John on 9/28/2021.
**** 9/14/2021 |  | OIT |  | Landing server for Agency File Transfers |  | 2021-10-06 | SS | 10/6/2021 - MOVEit zone will be utilitzed.
***** |  | DOT |  | RSU Certs Refresh |  | 2021-10-15 | JC | Design is validated.
2020-02-13 |  | TRE.Tax |  | Tax Analytics |  | 2020-05-04 | BXA | Design reviewed, zoning to be done
2021-10-15 |  | TRE.Taxation |  | Tableau |  | 2021-10-21 | JC | 10/21/21 - We'll show diagram to security on 10/26 and CP at design discussion on 10/27.
eReview 3/25/21 |  | TRE.Taxation |  | IVR Upgrade Project |  | 2021-09-28 | RL | 9/14/2021 @ 3:45PM - Email was sent by Roger notifying TRE of next step, i.e. to complete a Physical System Architecture Review (PSAR) form.
**** |  | DOC |  | NetMotion VPN |  | 2021-10-29 | RL | 10/29/2021 - Confirmed with Gary that he knows OK to PSAR to finalize the Netmotion VPN SAR process. He's not sure he's ready to do that yet, though...
eReview 10/22/2021 |  | TRE.DORES |  | Electronic Employer Filing Application For Informational Returns Project |  | 2021-11-01 | RL | pretty standard NICUSA implementation, take directly to J&D
eReview 5/24/2021 |  | DRBC |  | OPRA Webform Project |  | 2021-09-20 | BXA | Diagram ready for Denise and John
****No LSAR |  | CRC |  | Migration of MMP from DOH to CRC (Cannabis Regulatory Commission) |  | 2021-10-14 | BXA | Migration to occur 10/29 - 10/31
eReview 10/21/2021 |  | TRE |  | Treasurer’s Office Financial Literacy Program Project |  | 2021-11-10 | JC | 11/9 - Design Validated
2021-09-23 |  | NJSP |  | Expungement solution Part 2 - The New Coke |  | 2021-11-08 | JC | Will show to Denise and John on 11/9 again - need to confirm the Expungement and Kofax connex are actually at NJSP
eReview 11/1/2021 |  | TRE.DORES |  | Electronic Fax Filing Service |  | 2021-11-09 | RL | email sent to project team, please complete the C-IR
2021-10-14 |  | DOT |  | M365 Manage Plus |  | 2021-11-16 | SS | 11/16/2021 -D&J ok'd.
eReview 10/6/2021 |  | NJSP |  | Retired Police Officer system |  | 2021-11-16 | SS | 11/16/2021 - D&J ok'd.
2021-09-23 |  | NJSP |  | Veoci Deployment Mgmt solution |  | 2021-11-22 | SS | 11/22/2021 - Sent myNJ response wrt step 2b. If all agreen, then we are good. This is ok'd by D&J on 10/12.
eReview 9/15/2021 |  | TRE.Pensions |  | Thomson Reuters Project |  | 2021-11-29 | RL | Tue 11/23/2021 2:31 PM – Roger requested meeting to discuss the HTTP POST && Mon 11/29/2021 8:45 AM – Roger asked John Tripp to confirm CLEAR (MFA) uses SSL/TLS over port 443
2021-11-18 |  | TRE/TAX |  | Axon Body Worn Cameras |  | 2021-11-30 | JC | Validated after showing to Denise and John on 11/30
eReview 12/3/2021 |  | NJCCIC |  | Cybersecurity Risk Assessment Platform - Security Studio |  | 2021-12-07 | JC | 12/7 - Design Validated
|  | OIT |  | Alteris Upgrade from 8.2 to 8.6 |  | 2021-12-14 | JC | 12/14 - Design validated after running by OIT ISU
2021-10-28 |  | TRE.OSC |  | Granicus |  | 2021-11-01 | BXA | Working on MFA and Third Party Email
eReview 8/3/21 |  | CBVI |  | inFormed - Case Management System |  | 2021-12-21 | SS | 12/15/2021 - Denise confirmed that diagram now looks good. Ready to show Denise and John
eReview 10/21/2021 |  | LWD |  | Electronic Licensing and Inspection Tracking System (eLITS) Project |  | 2021-12-21 | SS | 12/21/2021 - Can show to Denise and John as FYI, there is nothing new to review.
eReview 12/16/2021 |  | NJCCIC |  | Chainalysis System Project |  | 2021-12-17 | JC | Jim to respond
2021-12-02 |  | LWD |  | D4AD - Phases 1 & 2 |  | 2022-01-03 | JC | 12/14 - Nimit at LWD answered our addional questions; show to ISU on 1/4/2022
2021-12-16 |  | DOT |  | Veeder Root Web Server (Console) |  | 2022-01-28 | JC | 1/25 - Design Validated
eReview 3/31/21 |  | DCF |  | Online Policy application migration |  | 2022-02-01 | SS | 2/1/2022 - Ready to show Security
eReview 12/21/2021 |  | TRE/Tax |  | C-LSAR for Treasury/Taxation Digital Tax Map Review Application Project |  | 2022-01-31 | SS | Design validated, passed on info from Carl Sebestyen.
eReview 1/27/2022 |  | NJSP |  | Overtime Software Project |  | 2022-02-09 | SS | 2/15/2022 - Ready to show security
*** |  | DCA |  | USFHEA - ARP Portal Integration |  | 2022-02-10 | SS | 2/15/2022 - Design validated.
eReview 1/19/2022 |  | NJSP |  | DMI ArcGIS project |  | 2022-04-11 | SS | 4/8/2022 - Desing validated email sent out.
2022-03-10 |  | TRE/Tax |  | Tax Printing and Mailing Solution upgrade |  | 2022-04-11 | SS | 4/6/2022 - Design validated email out.
*** |  | LWD |  | Tableau Collab |  | 2022-04-04 | JC | Check with Barbara on this..
*** |  | DOE |  | Orphaned SQLServer (Criminal History |  | 2022-04-07 | JC | John R responded with some additional info; sent him the current diagram
eReview 3/22/2022 |  | DOE |  | Teacher Certification Information System (TCIS) Salesforce |  | 2022-04-19 | SS | 4/28/2022 - Provisional ok from Barry, OHSP responded that Salesforce sign-in is approved.
eReview 3/16/2022 |  | LWD |  | Bank Replacement project |  | 2022-04-19 | SS | 4/19/2022 - Sent email, will call John Tidd for other less important questions.
2022-04-14 |  | TRE/Tax |  | Avaya CC Elite Digital System |  | 2022-05-10 | JC | Project is validated
eReview 4/22/2022 |  | DOE |  | Google Suite Project |  | 2022-05-02 | JC | Sent follow up to Shashi at DOE
2022-04-28 |  | DOH |  | Report Hub (Tableau) |  | 2022-05-02 | SS | 5/5/2022 - Sent out revised diagram and revised text for Chris to confirm once again.
eRevew 4/6/2022 |  | OIT |  | DocuSign Data and Reporting - AWS QuickSight project |  | 2022-05-25 | SS | 5/24/2022 - All good with security
**** |  | LWD |  | TDI/FLI project with Office of Innovation |  | 2022-06-07 | SS | 6/7/2022 - Showed security – ok
*** |  | OIT |  | DOTNET DEV Servers for Treasury |  | 2022-05-31 | JC | This project to be presented at today's Architecture and Security Review meetup (5/31)
**** |  | OIT |  | Altiris Upgrade Phase 2 |  | 2022-05-31 | BXA | Emailed RoseAnn and Rob about checking contention isssue with ZIA and Altiris sharing a zone.
eReview 12/14/2021 |  | TRE/Tax |  | IDEMIA Livescan System Project |  | 2022-06-08 | RL | notified Ryan Villaroman that's OK to fill out PSAR form
eReview 6/16/2022 |  | DOT |  | PAT application TomEE migration |  | 2022-06-21 |  | We don't typically do design for TomEE migration
eReview 9/13/2021 |  | NJSP |  | High Def Micro Video Downlink System - Vislink |  | 2022-06-13 | RL | Tue 6/7/2022 2:46 PM – Status from Portal Team: No news to report. You can check back if you haven't heard anything in a couple months (August)
eReview 6/23/2022 |  | MVC |  | Case Management System |  |  | JC
* |  | MVC |  | BizTalk 2020 Upgrade |  | 2022-06-24 | JC | Had meeting on 6/24/2022 regarding diagram walkthrough. Will review.
eReview 12/20/2021 |  | TRE/DOI |  | Multi Asset Analytics Tool (MAAT) |  | 2022-07-06 | RL | Ready for Security Meetup review. Need to schedule it.
2022-06-09 |  | MVC |  | EDDL-New Web Client |  | 2022-06-24 | JC | Held Meeting with Scott and Ron Parkum at IDEMIA - will review information and provide a polished account of notes furiously taken.
eReview 6/22/2022 |  | DEP |  | FFS Wildfire Risk Assessment portal |  | 2022-06-28 | SS | 7/5/2022 - ready for security.
*** |  | LWD |  | WHATS - server migration to EPC (Managed) |  | 2022-06-24 | JC | Design (with MWG) validated on 7/19/2022
2021-11-04 |  | CRC |  | Tableau |  | 2022-07-05 | JC | Sent update to CRC and AVAAP personnel - 5 SN tickets
eReview 5/26/2022 |  | OIT |  | SimpliGov |  | 2022-06-21 | BA | BA has asked Chandra to put his diagram in the IR and submit
***** |  | MVC |  | FM5 digitization w/ special guest Docusign |  | 2022-07-29 | JC | Ready for security meetup on 8/2
2022-07-28 |  | OHSP |  | RUMBLE |  | 2022-08-02 | JC | Validated the design on 8/2
eReview 7/14/2022 |  | LWD |  | Apprenticeship RTI |  | 2022-08-01 | SS | 8/1/2022 - Ready for security
2022-04-28 |  | OPD |  | Case Management Upgrade |  | 2022-08-04 | RL | Wed 8/3/2022 8:54 AM – Kyle SENT meeting INVITE
eReview 8/2/2022 |  | L&PS |  | ABC Emergency Permits |  | 2022-08-05 | JC | Ready for Security Meetup on 8/9
2022-06-30 |  | DHS/DMAHS |  | Provider Operational Data Store |  | 2022-08-17 | SS | 8/16/2022 - BA kindly presented to Security on SS’s behalf. Good to go.
eReview 8/18/2022 |  | TRE/Tax |  | Property Tax Reimbursement Application |  | 2022-08-23 | SS | 8/23/2022 - LSAR follow-up sent. Show to security this afternoon.
**** |  | CSC |  | LEE Prep Registration |  | 2022-08-18 |  | BA sent email asking for diagram
2022-08-25 |  | LPS/OAG |  | MS Dynamics CRM Thingy |  | 2022-08-25 | JC | Welcoming (Though hopefully not too welcoming) Packet Sent
2022-06-23 |  | NJSP |  | ALPR Cloud Migration (Puppy Chow) |  | 2022-08-25 | JC | Diagram we sent to NJSP is correct - probably can show to security on 8/30.
2022-06-23 |  | NJSP |  | OPS Network - Missing pers / Waterfront |  | 2022-09-16 | RL | 9/13/2022, sent Anthony the go ahead for C-IR form with the Validated Design diagram | DSFC Anthony Zoppina -- "ease of access for users " issues
fast track 3/18/2022 |  | DOE |  | Tomcat Upgrade LSAR |  | 2022-08-22 | BXA | Design validated, ticket opened
2022-09-22 |  | DCA |  | UAP One Stop Portal |  | 2022-10-11 | SS | 10/6/2022 - showed Security… OK
2022-09-22 |  | DOH |  | Microsoft Dynamics & Power Portal Implementation Platform |  | 2022-10-05 | BXA | Reviewed, responded
2022-05-12 |  | DCA |  | Daniel's Law Portal Project |  | 2022-09-21 | JC | We will show the new diagram (sent on 9/20) to ISU on 10/4
|  | BPU |  | Clean Energy Whole House Pilot Program WHPP |  | 2022-10-17 | BXA | LSAR held, will show diagram to Security 10/17
2022-08-11 |  | LWD |  | Drone Surveillance |  | 2022-10-11 | SS | 10/7/2022 – Asked SAR Meeting what the next step should be for this project as there is nothing really for “Implementation Review”.
*** |  | DOH |  | VERI |  | 2022-10-17 | BXA | Asked Eric Bauer if Wednesday at 10 a.m. would work
eReview by 11/1/2022 |  | DOC |  | DOC TomEE Migration - Offender Search |  | 2022-10-25 | RL | mail received from SARmeeting : Electronic Review - TomEE: DOC Offender Search Engine TomEE Migration
eReview 7/26/2022 |  | TRE/Admin |  | Vehicle Tracking Geotab |  | 2022-10-04 | SS | 10/3/2022 - Received responses to LSAR follow-up.
**** |  | OIT |  | Payroll Apps - Scanner Addition |  | 2022-11-16 | BXA | Will re-present this on 11/22.
eReview 9/8/2022 |  | DOH |  | Electronic Signatures DocuSign |  | 2022-11-22 | SS | 11/22/2022 - ready to show security...
2022-11-21 |  | TRE.Pensions |  | Health and Welfare Benefit Admin Service |  | 2022-11-22 | BXA | Validated 11/29/2022
2022-10-13 |  | DOC |  | Citrix Upgrade |  | 2022-11-18 | RL | Thu 11/17/2022 8:21 PM - Terence deferred to Citrix rep (Nam Nguyen) for Denise's questions about HA / load sharing
2022-06-09 |  | NJSP |  | Intell PenLink |  | 2022-11-15 | SS | 11/14/2022 - JT's email - The subnet has been provisioned to Brett and his team by Vic Staniec as of this afternoon.
2021-05-13 |  | LWD |  | DOL Audit Management Software (TeamMates) project (C-LSAR) |  | 2023-01-05 | RL | 1/5/2023 - Poked John
2022-07-14 |  | DOL |  | UI App Rewrite (RCC to ClaIMS) |  | 2022-12-21 | BXA | Received diagram
eReview 5/25/2022 |  | DEP |  | Motorola Flex Computer Aided Dispatch (CAD) |  | 2022-12-06 | BXA | Waiting on database decision
2022-12-01 |  | DOL |  | UI Modernization – Claimant Experience Pilot |  | 2023-02-09 | BXA | met with the team, waiting for their copy of the diagram
eReview 6/23/2022 |  | NJSP |  | StopIt |  | 2023-02-21 | RL | Emailed NJSP StopIt team with OK to proceed with C-IR form.
2022-12-30 |  | OHSP |  | Cobalt Strike |  | 2023-02-28 | SS | Sent LSAR follow-up, should be ready for Security.
2023-01-26 |  | TRE Dores |  | DCR Replacement Project |  | 2023-02-08 | JC | Archana Bajpai at DORES sent us a diagram - reviewing now
eReview 3/2/2023 |  | LWD |  | NJ Career Central |  | 2023-04-05 | SS | 4/4/2023 - reviewed with Security – OK
2022-03-24 |  | DEP |  | Electronic Submission of Event Data (DPCC & TCPA reports) |  | 2022-12-22 | RL | Rich provided final diagram. Phyllis (Systemetrix) still needs to work out scanning w/ OIT Mcafee Gateway admins
eReview 4/10/2023 |  | TRE/DORES |  | Enterprise Payment API Enhancement |  |  | BXAL
eReview 10/14/2022 |  | LWD |  | eForms and Workflow Automation |  | 2023-05-16 | RL | sent precis & diagram out to A&S team for eReview since this is well known SimpliGov SaaS
2023-03-09 |  | DHS/DoAS |  | Accuity Asset Verification Services |  | 2023-05-03 | SS | 5/3/2023 - Sent FYI of project to Security (all existing architecture – Safesforce - just adding api call)
eReview 1/31/2023 |  | DEP |  | Geotab Telematics Devices to monitor Electric Vehicles |  | 2023-04-05 | SS | Marie asked if this was validated, bringing it to our attention. Will followup.
2023-04-27 |  | LWD |  | Minor Working Papers |  | 2023-05-16 | SS | 5/16/2023 - Emailed project to Security team for eReview
eReview 4/10/2023 |  | OIT |  | DR Essential Support Function tracking system |  | 2023-04-20 | JC | Had a meeting with KK, Randy, and the DOTNET team. Sent the diagram template
eReview: 12/21/22 |  | TRE Pensions |  | TRE Pensions T3112 Death Audits Project |  |  |  | placeholder
eReview 3/1/23 |  | BPU |  | BPU Infoshare Database Management System Upgrade |  |  |  | The design for BPU’s upgrade project was validated in March 2023, and the VMs were built in April.
*** |  | OIT |  | ExaCC X9 machine |  | 2022-12-21 | BXA | Need to make final diagram
2023-04-27 |  | OIT.DigSvcs |  | Website Accessibility Checker - SiteImprove |  | 2023-05-31 | RL | SolArch discussed: decided no need for any of these: Custom URL, SoNJ email domain, WAF. Reasoning: users/customers are all SoNJ employees NOT the public. As such they will be aware that this is an outside vendor service, hence not needing to see SoNJ domain in email nor URL. WAF is responsibility of the vendor to protect their own site. Sent John the above summary, notified him OK to proceed to C-IR, attached Visio, CC’d Portal Admins.
2023-05-11 |  | LWD |  | Determination and Status Hub (DASH) - part of modernization project |  | 2023-06-13 | SS | Ready for security
2023-03-23 |  | DCF |  | Office Space Planning - OfficeSpace |  | 2023-06-29 | SS | 06/26/2023 – validated and email sent to David Peck
TIP held 12/6/2021 |  | DEP |  | Warehouse Management System (WMS) in the Cloud (Slingshot) |  | 2022-12-07 | RL | Victor needs to add myNJ to diagram, and when ready, use it for C-IR
2022-03-24 |  | DOT |  | SplashTop Remote Access Support |  | 2023-07-05 | SS | In production, sent them email with validated design, SAR team aware.
eReview 5/25/2023 |  | NJSP |  | Concealed Carry Permits |  | 2023-06-27 | JC | Validated on June 27, 2023
eReview 5/17/2023 |  | NJSP |  | Sprout Social |  | 2023-07-11 | JC | Going to show at A&S Review today (7/11)
2023-06-08 |  | LWD |  | Tableau Collaboration |  | 2023-07-11 | JC | Going to show at A&S Review today (7/11)
2023-04-13 |  | LPS |  | L&PS Enterprise Law Management Project (WiseTime & TeamConnect) |  | 2023-07-26 | RL | Roger sent notice – OK for C-IR
eReview 7/7/2023 |  | TRE |  | Admin Printing Digital Storefront Website Project |  | 2023-07-17 | JC | Diagram submitted on 7/17/2023 - JC to review
|  | NJSP |  | Port Security Project |  | 2323-04-20 | JC | Port Security Project is being continued again as per a US Supreme Court descision
2021-03-03 |  | MVC |  | Driver Video Conferencing Project |  | 2023-08-03 | JC | Design validated - added an authentication service (built on AWS EC2 instances) that was publicly facing - app was previously validated but the authentication service was on an internal server, unreachable from the outside

## Dormant
LSAR Date | Department | Project | Design Needed? | Held? | Complete? | Notes
2017-08-10 | DOT | ProjectWise Cloud hosting | if myNJ
| L&PS/DCA | Project ULTRA- Dynamics 365 | Y |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\LPS.DCA-ProjectUltra-Dynamics-AzureMaaS\LPS.DCA-ProjectUltra-Dynamics-et-alia.docx
*** | TRE.OMB | WASP - LBAM Asset Tracker | Y |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active%20Projects\TRE.OMB.WASP-LBAM\TRE.OMB-WASP-LBAM.docx
2018-03-08 | DEP | Esri ArcGIS cloud-based emergency system | Y |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DEP.ArcGISCloudForEmergencies\DEP.AGOCloudBuildout.docx
2017-06-22 | DHS | Kronos | Y |  |  | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\DHS.Kronos\DontBlameUsWeVotedForKronos-STATUS.docx
2018-08-09 | LPS-DGE | ONE Project (Oracle Cloud Services) | Y | N | N | file:///Q:\PMC\IPP\SolutionsArchitecture\Active Projects\LPS.DGE-ONEProject\LPS.DGE-ONEStatus.docx
2018-11-15 | DOC | DeptCOR ERP Hosting Change to GSS | Y |  |  | DEPTCOR_STATUS
| TRE/Pensions | Medical Claims Reviewer |  |  |  | 8/14/2019 RL | Karen: TIP meeting scheduled for 8/26
2018-07-12 | DOC | Infoshare Upgrade Phase 2 | Y | N | N |  | 02/11/2019 – received answer to last week’s email – reviewing now, New phase TIP on April 15th for Phase 2
| DOL/LWD | Security Concerns with ICON Application |  |  |  | 7/24/2019 JC | 7/24/2019 – Going to LSAR
** | OIT | System diagram builds for ISU |  |  |  |  | 05/20/2019 – Steve says he wants his engineers to make the diagrams, and us to ingest them
2019-10-24 | OHSP | CCIC ForeScout NAC | 2019-11-25 | BA | Mon 11/25/2019 Email to Jennifer Pullen advising that this project was going to be discussed at exec level
2017-12-11 | L&PS | Integrated Drug Awareness Dashboard |  |  | 06/10/2019 – Hagen sent email asking Joy for control and data flow
| TRE | Single Sign on for WASP AssetCloud | 2019-08-28 | RL | 9/6/2019 10:41 AM – Barbara email to MVC: You're welcome to stand up your own ADFS instance
2020-09-10 | DCF | Transitions4Youth website migration | 2020-09-28 | BXA | 9/24/2020 - refer them to Lynne to get a mini-bid for the Yutes
*** | OIT | SDDC - Dell/Vmware Cloud Foundation | 2019-12-05 | BXA | Meeting was held, cool features are on hold, most chassis will be used for workload relief.
| OIT | ServiceNow-ServiceMapping eCATS | 2020-08-24 | SS | Asked Sri to confrim the std. diagram for all TomEE migrations, showing F5s.
?? | TRE/DORES | MobileFrame | 2020-10-22 | SS | Project canned in December 2020, as per Dario
2019-11-20 | DOT | Outdoor Advertising | 2019-11-25 | BXA | 11/21/2019 – Sent two emails – one regarding general follow-up, and one regarding myNJ.
| DOT | TAMS (Ronald McDonald) | 2020-08-25 | BXA | Sigh.
| DOT | eBuilder | 2020-08-25 | BXA | CR signed off on this. Gary Z ceased communications.
2019-03-01 | DOT | Crash Records ARD database in Cloud | 2021-06-15 | SS | 6/15/2021 - Chris replied – project suspended until funds available
2021-09-09 | DOT | B2GSoon | 2022-08-01 | JC | Asked Komila for an update
*** | OIT | Cisco DUO POC | 2022-11-28 | BXA | POC scrapped
*** | DCF.DOW | Alloy Collab Space for Domestic Violence Prevention | 2023-05-31 | BXA | Sent C. Mahan another email to see if project still on
**** | MVC | EDDL Facial Recognition Upgrade | 2023-05-31 | BXA | MVC still waiting on specs from IDEMIA for the new VMs
2018-08-23 | DOC | eMAR (Electronic Medication Administration Records) | 413508 | JC | My data entry mistake regarding the year will ironically be correct in 3032 AD, so I'm leaving it in.
2018-10-25 | OIT | Service Now! Phase 2 | 2019-09-30 | BA | Meeting scheduled for 09/16/2021
2019-10-24 | DOT | DOT MS2 Traffic Counts Processing Software | 2020-01-14 | RL | 1/14 -> Still active, but as far as our responsibility at this point - DORMANT
2019-11-14 | LWD | ICON Modernization | 2021-01-19 | RL | Mon 1/11/2021 2:52 PM - Kevin confirmed they are still waiting on Project X to leverage that Web Service
2020-11-19 | LPS/DGE | DGE ONE Project (Pega) | 2022-03-07 | RL | 03/14/2022: Learned from Lynne Gash that the DGE ONE project has hit a very rough patch. Details @ 11.
2021-08-12 | LPS | Infoshare Upgrades | 2022-01-03 | JC | Sent another email to Chris Ward asking for the existing Infoshare IP Address
2022-03-10 | DOC | Cisco Video Visitation System | 2022-03-28 | JC | Sent Keith Mercantante an email about who to work with on this project since Gary M is persona non-grata
2021-05-27 | DMAVA | Veteran's Home Electronic Medical Records Project | 2022-05-23 | SS | 5/23/2022- Toni B says Vendor cannot provide statutorily required certifications.
eReview 12/30/2021 | DEP | Site Remediation and Waste Management Program (SRWMP) UIPath POC Workflow Project | 2022-03-15 | JC | Showed to ISU - need to confirm some things (see status sheet)
**** | DOH | Hospital Staff Scheduling - iNovar | 2022-04-29 | RL | Don Eckel: we're working through the procurement process. Most likely this will be in Q3 of this year.
2022-06-02 | NJ SPB | State Parole Board (SPB) Computer Aided Dispatch (CAD) | 2022-09-26 | RL | Mon 9/26/2022 8:12 AM: (email from Joe Gogan) our Computer Aided Dispatch project. At this point, it is on hold until after the new year.
2022-04-14 | TRE/DRM | (Risk) Claims and Case Management System | 2023-02-21 | RL | 2/14/23 - Rcvd confirmation from MWG Admin & vendor (Phyllis) that MWG will be scanning downloads. Ready for Sec'ty review.
2023-02-08 | OIT | Xerox Multi-function printers | 2023-03-21 | SS | 5/31/2023 - Summary of meeting from BA – There needs to be a discussion between Allison Davis, Shaiesta of OHSP and Toni regarding security.
**** | CCC | IBM iSeries Upgrade | 2022-10-17 | BXA | Recieved response to questions, need to review and respond.